## Testing
Company code | Plant code | New/Existing | Prj Type | Plant Description | Material Master Testing status | WBS CODE | PS Testing status | SAP PR | SAP PO NUMBER | MM - PUR Testing status | GRN/MIR7 Status | SES | MIR7 | MM- IM Testing status | FI Testing status GRN | FI Testing status SES | SD Testing status | Client Billing | PM Testing status | Moved to Prod | TR NO WITH DETAILS | Incident No
3000 | 3064 | NEW | EPC | BWSSB , V Valley Bengaluru- EPC | Done | E-175 | Done | Service :--10000533, 10000534 Material :- 10000535 Manual PR as Auto PR not working- 1000000265 | Service :-4000000164 Material :- 1000000353 | Done | GRN 103 - 5000000970; 105 -5000000971 MIR7 - 5105600462 | 1000000464 | 5105600464 | DONE | 5100000301-Ok 5100000303-Ok | Done | SO:130 : HSN Code not maintain in Material Master |  |  |  | DS4K903273- MM_09052023_Plant 3064-BWSSB ,V Valley Bengaluru STP- EPC_RD DS4K903279 FI_MM_BWSSB Plant Creation_10.05.2023 DS4K903289 : PS_11052023_PlantConfig3064_RS DS4K903275 VEPL_SD_NEW PLANT 3064_100523 | INC-2023-00XXX
3000 | 3033 | EXISTING | EPC | PCMC-24 X 7 Water Supply | Done | E-173 | Done | Material- 1000000263 Service- 4000000201 | 6000000024 | Done | GRN 103 - 5000000972; 105 -5000000973 MIR7 - 5105600463 | 1000000453 | 5105600461 | DONE | 5100000300-Ok 5100000302-Ok | Done | SO: 131: HSN Code not maintain in Material master

## 3063-RWSSD
Plant Name & Address |  | RWSSD, Karnataka O & M |  |  |  |  | Company Code | 3000 | Plant Code | 3063
[7 empty] | Profit Center | 306301 | GSTN | -
Sr. No. | Responsible | Description | Days | Plan Start | Plan End | Actual Start | Actual End | Status | % completed | Remarks
1 | VEPL | Providing of key data in the shared template for Plant Creation | 1 | 25-04-2023 | 26-04-2023 | 25-04-2023 | 25-04-2023 | Completed | 100%
2 | VEPL | Finalising Users and Authorisation |  | 25-04-2023 | 2023-10-05 | 28-04-2023 |  | In Progress
3 | VEPL / PwC | Collected Data to be reviewed by Finance Co-Ordinate | 1 | 25-04-2023 | 26-04-2023 | 25-04-2023 | 25-04-2023 | Completed | 100%
4 | PwC MM | Creation of Plant Code in SAP | 1 | 25-04-2023 | 26-04-2023 | 25-04-2023 | 25-04-2023 | Completed | 100%
5 | VEPL | Plant code review by VEPL Team | 1 | 26-04-2023 | 27-04-2023 | 26-04-2023 | 27-04-2023 | Completed | 100%
6 | VEPL Finance | Profit Center creation | 1 | 26-04-2023 | 27-04-2023 | 26-04-2023 | 27-04-2023 | Completed | 100%
7 | VEPL Finance | Cost Center creation |  | 26-04-2023 | 27-04-2023 | 26-04-2023 | 27-04-2023 | Completed | 100%
8 | PwC | Modulewise baseline Configuration | 4 | 27-04-2023 | 2023-01-05 | 27-04-2023 | 2023-01-05 | Completed | 100%
|  | MM | [6 empty] | Done
|  | FICO | [6 empty] | Done
|  | SD | [6 empty] | Done
|  | PS | [6 empty] | Done
|  | PM | [6 empty] | Done
9 | PwC | Unit Testing | 2 | 2023-01-05 | 2023-03-05 | 2023-01-05 | 2023-03-05 | Completed | 100%
|  | MM | [6 empty] | Done
|  | FICO | [6 empty] | Done
|  | SD | [6 empty] | Done
|  | PS | [6 empty] | Done
|  | PM | [6 empty] | Done
10 | PwC | Transfer to Quality System | 1 | 2023-03-05 | 2023-04-05 | 2023-03-05 | 2023-03-05 | Completed | 100%
11 | VEPL | CTM Testing (UAT/Regression Testing) | 3 | 2023-04-05 | 2023-07-05 | 2023-03-05 | 2023-04-05 | Completed | 100%
12 | VEPL / PwC | Incident resolution and closure | 2 | 2023-07-05 | 2023-09-05 | 2023-04-05 | 2023-04-05 | Completed | 100%
13 | VEPL / PwC | Uploading of TR Forms in VOICE Tool | 1 | 2023-10-05 | 2023-11-05 | 2023-04-05 | 2023-04-05 | Completed | 100%
14 | VEPL | Movement of TR to PRD | 1 | 2023-11-05 | 2023-12-05 | 2023-04-05 |  | In progress
15 | VEPL | Providing of authorisation to Users | 1 | 2023-11-05 | 2023-12-05 |  |  | Yet to Start
16 | VEPL | Production Master data Maintenance | 2 | 2023-12-05 | 14-05-2023 |  |  | Yet to Start
17 |  | Ready for use in Production
User Testing
MM
FI
| PS |  | Done / UT Success mail recieved | Done / UT Success mail recieved
PM
| SD |  | Done | Done
TR No.s | Sequence | TR No.s | TR Description | TR Description | TR Forms
MM | 1.1 | DS4K901984 | MM_17102022_Plant - 3052(pench)_HN | MM_17102022_Plant - 3052(pench)_HN
| 1.2 | DS4K902237 | MM_14112022_quality inspection setting_HN | MM_14112022_quality inspection setting_HN
| 1.3 | DS4K902245 | MM_14112022_Pench 3052 name change_HN | MM_14112022_Pench 3052 name change_HN
| 1.4 | DS4K902221 | MM_10112022_Storage Location for Pench O&M 3052_RD | MM_10112022_Storage Location for Pench O&M 3052_RD
| 1.5 | DS4K902241 | MM_14112022_St Loc Change NMC PENCH O&M 3052_RD | MM_14112022_St Loc Change NMC PENCH O&M 3052_RD
FI | 2.1 | DS4K902145 | FICO_04112022_Pench Plant Configuration | FICO_04112022_Pench Plant Configuration
PS | 3.1 | DS4K902009 | PS_19102022_3052 Plant Configuration_RS | PS_19102022_3052 Plant Configuration_RS | Recieved
| 3.2 | DS4K902253 | PS_15112022_3052_CONFIG_SETTING_ZV02 | PS_15112022_3052_CONFIG_SETTING_ZV02
PM | 4.1 | DS4K902011 | PM_19102022_3052 Plant Configuration_NM | PM_19102022_3052 Plant Configuration_NM
SD | 5.1 | DS4K901990 | SD: Plant 3052 Configuration | SD: Plant 3052 Configuration
What is pending | SRN | VEPL Bhagrashree | Harshada | Harshada | Done
| Invoice Parking | VEPL Bhagrashree | Harshada | Harshada | Done
| FI Invoice Posting : SRN | VEPL : Manish Daga | Akash | Akash
| FI Invoice Posting : GRN | VEPL : Manish Daga | Akash | Akash
|  | 1 | Balance WRICEF | Balance WRICEF
|  | 2 | Balance Plants | Balance Plants
|  | 3 | Handover Documentation | Handover Documentation
|  | 4 | Incident | Incident

## 3064-BWSSB
Plant Name & Address |  | BWSSB , V Valley Bengaluru STP- EPC |  |  |  |  | Company Code | 3000 | Plant Code | 3064
[7 empty] | Profit Center | 306401 | GSTN | 29AADCV0032H1ZK
Sr. No. | Responsible | Description | Days | Plan Start | Plan End | Actual Start | Actual End | Status | % completed | Remarks
1 | VEPL | Providing of key data in the shared template for Plant Creation | 1 | 2023-08-05 | 2023-09-05 | 2023-08-05 | 2023-08-05 | Completed
2 | VEPL | Finalising Users and Authorisation |  | 2023-09-05 |  | 2023-09-05 |  | In Progress
3 | VEPL / PwC | Collected Data to be reviewed by Finance Co-Ordinate | 1 | 2023-09-05 | 2023-10-05 | 2023-09-05 | 2023-09-05 | Completed
4 | PwC MM | Creation of Plant Code in SAP | 1 | 2023-10-05 | 2023-11-05 | 2023-10-05 | 2023-10-05 | Completed
5 | VEPL | Plant code review by VEPL Team | 1 | 2023-11-05 | 2023-12-05 | 2023-10-05 | 2023-10-05 | Completed
6 | VEPL Finance | Profit Center creation | 1 | 2023-12-05 | 2023-12-05 | 2023-10-05 | 2023-10-05 | Completed
7 | VEPL Finance | Cost Center creation |  | 2023-12-05 | 2023-12-05 | 2023-10-05 | 2023-10-05 | Completed
8 | PwC | Modulewise baseline Configuration | 4 | 15-05-2023 | 19-05-2023 | 2023-11-05 | 2023-12-05 | In Progress
|  | MM | [5 empty] | Completed
|  | FICO | [5 empty] | Completed
|  | SD | [5 empty] | Completed
|  | PS | [5 empty] | Completed
|  | PM | [5 empty] | Completed
9 | PwC | Unit Testing | 2 | 19-05-2023 | 20-05-2023 |  |  | Yet to Start
MM
FICO
SD
PS
PM
10 | PwC | Transfer to Quality System | 1 | 20-05-2023 | 20-05-2023 |  |  | Yet to Start
11 | VEPL | CTM Testing (UAT/Regression Testing) | 2 | 22-05-2023 | 23-05-2023 |  |  | Yet to Start
12 | VEPL / PwC | Incident resolution and closure | 1 | 23-05-2023 | 23-05-2023 |  |  | Yet to Start
13 | VEPL / PwC | Uploading of TR Forms in VOICE Tool | 1 | 23-05-2023 | 24-05-2023 |  |  | Yet to Start
14 | VEPL | Movement of TR to PRD | 1 | 24-05-2023 | 24-05-2023 |  |  | Yet to Start
15 | VEPL | Providing of authorisation to Users | 0 | 24-05-2023 | 24-05-2023 |  |  | Yet to Start
16 | VEPL | Production Master data Maintenance | 1 | 24-05-2023 | 25-05-2023 |  |  | Yet to Start
17 |  | Ready for use in Production |  | 25-05-2023