## Sheet1
Level (WTUFE) | Proj Def/WBS Code (PSPID/POSID) | INTERNAL PURPOSE (RWTXT-TXLINE) | Profile (PROFL) | Description (POWT1) (40 char) | Controlling Area (PROJ-VKOKR) | Company Code (VBUKR) | Plant (WERKS) | Factory Calendar (PROJ-KALID) | Profit Center (PRCTR) | Client (PROJ-ZZCLIENT) | Contract Type (PROJ-ZZCONTTYPE) | Defect Liability Period(in Months) (PROJ-ZZDEF_PERIOD) | Proj Type (PRART) | Planning Element (PLAKZ) | Acc Element (BELKZ) | Billing Element (FAKKZ) | Person Responsible (VERNR) | WBS Type (PRPS-ZZWBWTYP) | Service Material (PRPS-ZZSERVMAT) | Serial No (PRPS-ZZSRNO) | Tender Item No (PRPS-ZZTENITNO) | Original BOQ Qty (ZTPRPS_ADDL-ZZORBOQ) | Billable Variance BOQ Qty (ZTPRPS_ADDL-ZZBVBOQ) | Non Billable Variance BOQ Qty (ZTPRPS_ADDL-ZZNBVBOQ) | UoM (ZTPRPS_ADDL-ZZMEINS) | Original Non Billable BOQ Qty (ZTPRPS_ADDL-ZZORNBBOQ) | DC Rate (ZTPRPS_ADDL-ZZDCRT) | DC Amount | SP Rate (ZTPRPS_ADDL-ZZSPRT) | Internal MIS Billing Rate (ZTPRPS_ADDL-ZZMISRT) | Currency | Start Date | End date
| E-119 | 3056 HASSAN DBOT PROJECT | ZVGPLEP | 3056 -HASSAN DBOT PROJECT | 1000 | 3000 | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
1 | E-119 | 3056 HASSAN DBOT PROJECT | ZVGPLEP | 3056 -HASSAN DBOT PROJECT | 1000 | 3000 | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
2 | E-119-WS | 3056 HASSAN DBOT PROJECT | ZVGPLEP | 3056 -HASSAN DBOT PROJECT | 1000 | 3000 | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
3 | E-119-WS-01 | DPR PREPARATION | ZVGPLEP | DPR PREPARATION |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
4 | E-119-WS-01-01 | DETAILED SCHEME REPORT | ZVGPLEP | DETAILED SCHEME REPORT |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
5 | E-119-WS-01-01-01 | SUBMISSION OF DSR FOR REVIEW | ZVGPLEP | SUBMISSION OF DSR FOR REVIEW |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 8206913 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-01-01-02 | After submission of Final 5 Sets | ZVGPLEP | After submission of Final 5 Sets |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 2051728 |  | INR | 23.12.2022 | 23.12.2024
4 | E-119-WS-01-02 | CONSTRUCTION DOCUMENTS AND DRAWINGS | ZVGPLEP | CONSTRUCTION DOCUMENTS AND DRAWINGS |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
5 | E-119-WS-01-02-01 | Civil, Pipeline and building drawings | ZVGPLEP | Civil, Pipeline and building drawings |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 3437262 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-01-02-02 | Mechanical drawings | ZVGPLEP | Mechanical drawings |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 2864385 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-01-02-03 | Electrical drawings | ZVGPLEP | Electrical drawings |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 2291507 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-01-02-04 | INSTRUMENTATION AND CONTROL SYSTEM | ZVGPLEP | INSTRUMENTATION AND CONTROL SYSTEM |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 1718631 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-01-02-05 | Progress report submission | ZVGPLEP | Progress report submission |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 1145754 |  | INR | 23.12.2022 | 23.12.2024
4 | E-119-WS-01-03 | OPERATION AND MAINTENANCE MANUALS | ZVGPLEP | OPERATION AND MAINTENANCE MANUALS |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
5 | E-119-WS-01-03-01 | FIRST ISSUE PRIOR TO CHECK | ZVGPLEP | FIRST ISSUE PRIOR TO CHECK |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 4103457 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-01-03-02 | As built drawings and OandM Manuals | ZVGPLEP | As built drawings and OandM Manuals |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 1025864 |  | INR | 23.12.2022 | 23.12.2024
3 | E-119-WS-02 | CONSTR CD IW CP JW LAND ACQISITION | ZVGPLEP | CONSTR CD IW CP JW LAND ACQISITION |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
4 | E-119-WS-02-01 | CONSTRUCTION OF COFFER DAM CD | ZVGPLEP | CONSTRUCTION OF COFFER DAM CD |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-01-01 | AFTER COMPLETION OF FOUNDATION CD | ZVGPLEP | AFTER COMPLETION OF FOUNDATION-CD |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 1806891 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-01-02 | AFTER COMPLETION OF SUBSTRUCTURE CD | ZVGPLEP | AFTER COMPLETION OF SUBSTRUCTURE-CD |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 1806891 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-01-03 | AFTER COMPLETION OF SUPERSTRUCTURE CD | ZVGPLEP | AFTER COMPLETION OF SUPERSTRUCTURE -CD |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 2529648 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-01-04 | After Completion of Testing Rolling | ZVGPLEP | After Completion of Testing Rolling |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000049 |  |  | 1 |  |  | LS |  |  |  | 722756 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-01-05 | AFTER COMPLETION OF TRIAL RUN CD | ZVGPLEP | AFTER COMPLETION OF TRIAL RUN-CD |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000049 |  |  | 1 |  |  | LS |  |  |  | 361378 |  | INR | 23.12.2022 | 23.12.2024
4 | E-119-WS-02-02 | CONSTRUCTION OF INTAKE WELL IW | ZVGPLEP | CONSTRUCTION OF INTAKE WELL IW |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-02-01 | After Completion of Foundation | ZVGPLEP | After Completion of Foundation |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 1212925 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-02-02 | After Completion of Substructure | ZVGPLEP | After Completion of Substructure |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 1212925 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-02-03 | After Completion of Superstructure | ZVGPLEP | After Completion of Superstructure |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 1698095 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-02-04 | After Completion of Testing | ZVGPLEP | After Completion of Testing |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000049 |  |  | 1 |  |  | LS |  |  |  | 485170 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-02-05 | After Completion of Trial run | ZVGPLEP | After Completion of Trial run |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000049 |  |  | 1 |  |  | LS |  |  |  | 242585 |  | INR | 23.12.2022 | 23.12.2024
4 | E-119-WS-02-03 | LAYING OF CONNECTING PIPE LCP | ZVGPLEP | LAYING OF CONNECTING PIPE LCP |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-03-01 | CONNECTING PIPES FOR INTAKE WELL | ZVGPLEP | CONNECTING PIPES FOR INTAKE WELL |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-03-01-001 | AFTER COMPLETION OF FOUNDATION and SUPPLY | ZVGPLEP | AFTER COMPLETION OF FOUNDATION and SUPPLY |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 2133490 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-03-01-002 | AFTER COMPLETION OF SUBSTRUCTURE | ZVGPLEP | AFTER COMPLETION OF SUBSTRUCTURE |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 2133490 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-03-01-003 | AFTER COMPLETION OF SUPERSTRUCTURE LAYIN | ZVGPLEP | AFTER COMPLETION OF SUPERSTRUCTURE LAYIN |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 2986887 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-03-01-004 | After Completion of Testing refilling | ZVGPLEP | After Completion of Testing refilling |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000049 |  |  | 1 |  |  | LS |  |  |  | 853396 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-03-01-005 | After Completion of Trial run | ZVGPLEP | After Completion of Trial run |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000049 |  |  | 1 |  |  | LS |  |  |  | 426698 |  | INR | 23.12.2022 | 23.12.2024
4 | E-119-WS-02-04 | CONSTRUCTION OF JACK WELL JW | ZVGPLEP | CONSTRUCTION OF JACK WELL JW |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-04-01 | Construction of Jack Well | ZVGPLEP | Construction of Jack Well |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-04-01-001 | After Completion of Foundation | ZVGPLEP | After Completion of Foundation |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 8217893.5 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-04-01-002 | After Completion of Substructure | ZVGPLEP | After Completion of Substructure |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 8217893.5 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-04-01-003 | After Completion of Superstructure | ZVGPLEP | After Completion of Superstructure |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 11505050.9 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-04-01-004 | After Completion of Testing | ZVGPLEP | After Completion of Testing |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000049 |  |  | 1 |  |  | LS |  |  |  | 3287157.4 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-04-01-005 | After Completion of Trial run | ZVGPLEP | After Completion of Trial run |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000049 |  |  | 1 |  |  | LS |  |  |  | 1643578.7 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-04-02 | Construction of Electrical Sub Station | ZVGPLEP | Construction of Electrical Sub Station |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-04-02-001 | After Completion of Foundation | ZVGPLEP | After Completion of Foundation |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 1203539 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-04-02-002 | After Completion of Substructure | ZVGPLEP | After Completion of Substructure |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 1203539 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-04-02-003 | After Completion of Superstructure | ZVGPLEP | After Completion of Superstructure |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 1684954 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-04-02-004 | After Completion of Testing | ZVGPLEP | After Completion of Testing |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000049 |  |  | 1 |  |  | LS |  |  |  | 481415 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-04-02-005 | After Completion of Trial run | ZVGPLEP | After Completion of Trial run |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000049 |  |  | 1 |  |  | LS |  |  |  | 240707 |  | INR | 23.12.2022 | 23.12.2024
4 | E-119-WS-02-05 | Construction of Approach Bridge | ZVGPLEP | Construction of Approach Bridge |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-05-01 | After Completion of Foundation | ZVGPLEP | After Completion of Foundation |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 1450216.5 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-05-02 | After Completion of Substructure | ZVGPLEP | After Completion of Substructure |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 1450216.5 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-05-03 | After Completion of Superstructure | ZVGPLEP | After Completion of Superstructure |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 2030303.1 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-05-04 | After Completion of Testing | ZVGPLEP | After Completion of Testing |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000049 |  |  | 1 |  |  | LS |  |  |  | 580086.6 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-05-05 | After Completion of Trial run | ZVGPLEP | After Completion of Trial run |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000049 |  |  | 1 |  |  | LS |  |  |  | 290043.3 |  | INR | 23.12.2022 | 23.12.2024
4 | E-119-WS-02-06 | DEVLOP LAYOUT AT HEADWORKS | ZVGPLEP | DEVLOP LAYOUT AT HEADWORKS |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-06-01 | Construcuion of Compound wall | ZVGPLEP | Construcuion of Compound wall |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-06-01-001 | After Completion of Foundation | ZVGPLEP | After Completion of Foundation |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 1227313 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-06-01-002 | After Completion of Substructure Comp wa | ZVGPLEP | After Completion of Substructure-Comp wa |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 1227313 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-06-01-003 | After Completion of Superstructure Comp | ZVGPLEP | After Completion of Superstructure-Comp |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 1718237 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-06-01-004 | After Completion of Testing | ZVGPLEP | After Completion of Testing |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000049 |  |  | 1 |  |  | LS |  |  |  | 490925 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-06-01-005 | After Successful Completion of Trial run | ZVGPLEP | After Successful Completion of Trial run |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000049 |  |  | 1 |  |  | LS |  |  |  | 245462 |  | INR | 23.12.2022 | 23.12.2024
5 | E-119-WS-02-06-02 | Approach roads at headworks | ZVGPLEP | Approach roads at headworks |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X | [15 empty] | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-06-02-001 | After Completion of Foundation exc ARHW | ZVGPLEP | After Completion of Foundation exc ARHW |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 368194 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-06-02-002 | After Completion of Substructure ARHW | ZVGPLEP | After Completion of Substructure - ARHW |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 368194 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-06-02-003 | After Completion of Superstructure ARHW | ZVGPLEP | After Completion of Superstructure-ARHW |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000048 |  |  | 1 |  |  | LS |  |  |  | 515471 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-06-02-004 | After Completion of Testing | ZVGPLEP | After Completion of Testing |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000049 |  |  | 1 |  |  | LS |  |  |  | 147278 |  | INR | 23.12.2022 | 23.12.2024
6 | E-119-WS-02-06-02-005 | After Successful Completion of Trial run | ZVGPLEP | After Successful Completion of Trial run |  |  | 3056 | IN | 305601 |  |  |  | EC | X | X | X |  | Z01 | 2800000049 |  |  | 1 |  |  | LS |  |  |  | 73638 |  | INR | 23.12.2022 | 23.12.2024