## Sheet1
Company code | Plant code | New/Existing | Prj Type | Plant Description | Material Master Testing status | WBS CODE | SAP PR | PS Testing status | SAP PO NUMBER | MM - PUR Testing status | GRN/MIR7 Status | SES | MIR7 | MM- IM Testing status | FI Testing status GRN | FI Testing status SES | SD Testing status | Client Billing | PM Testing status | TR NO WITH DETAILS
3000 | 3063 | New | O & M | RWSSD, Karnataka - O &M | Done | E-172 | M- 1000000260 S- 4000000199 | Done | M- 1000000345 S- 4000000154 | Done | GRN 103 - 5000000915 105 - 5000000916 GI = 4900000840 PV = 4900000841 MIR7 - 5105600453 | 1000000428 | 5105600449 | DONE | 5100000289-Ok 5100000292-Ok | Done | SO: 127: | NA | NA | DS4K903233 MM_25042023_Plant 3063-RWSSD, Karnataka - O &M_RD DS4K903247 FI_MM_O&M Plant Creation_27.04.2023 DS4K903243 100 : 27042023_O&M_3063_RWSSDplantconfig_RS DS4K903235 PWCSD_1 VEPL_SD_Plant_RWSSD, Karnataka DS4K903249 PM_17122022_New O&M Plant Config_NM
3000 | 3035 | EXISTING | O & M | NIT-1 O&M | Done | E-171 | Material- 1000000258 Service- 4000000198 | Done | 6000000023 | Done | GRN 103 - 5000000917 105 - 5000000918 MIR-7 = 5105600452 | 1000000429 | 5105600450 | DONE | 5100000290-Ok 5100000291-Ok | Done | SO:128 | NA | NA
[6 empty] | 10 | 10 |  | 10 |  | 10 | 10 | 10 |  | 10 |  | 10 |  | 10

## Sheet2
Plant Name & Address |  | RWSSD, Karnataka O & M |  |  |  |  | Company Code | 3000 | Plant Code | 3063
[7 empty] | Profit Center | 306301 | GSTN | -
Sr. No. | Responsible | Description | Days | Plan Start | Plan End | Actual Start | Actual End | Status | % completed | Remarks
1 | VEPL | Providing of key data in the shared template for Plant Creation | 1 | 25-04-2023 | 26-04-2023 | 25-04-2023 | 25-04-2023 | Completed | 100%
2 | VEPL | Finalising Users and Authorisation |  | 25-04-2023 | 2023-10-05 | 28-04-2023 |  | In Progress
3 | VEPL / PwC | Collected Data to be reviewed by Finance Co-Ordinate | 1 | 25-04-2023 | 26-04-2023 | 25-04-2023 | 25-04-2023 | Completed | 100%
4 | PwC MM | Creation of Plant Code in SAP | 1 | 25-04-2023 | 26-04-2023 | 25-04-2023 | 25-04-2023 | Completed | 100%
5 | VEPL | Plant code review by VEPL Team | 1 | 26-04-2023 | 27-04-2023 | 26-04-2023 | 27-04-2023 | Completed | 100%
6 | VEPL Finance | Profit Center creation | 1 | 26-04-2023 | 27-04-2023 | 26-04-2023 | 27-04-2023 | Completed | 100%
7 | VEPL Finance | Cost Center creation |  | 26-04-2023 | 27-04-2023 | 26-04-2023 | 27-04-2023 | Completed | 100%
8 | PwC | Modulewise baseline Configuration | 4 | 27-04-2023 | 2023-01-05 | 27-04-2023 | 2023-01-05 | Completed | 100%
|  | MM | [7 empty] | Done
|  | FICO | [7 empty] | Done
|  | SD | [7 empty] | Done
|  | PS | [7 empty] | Done
|  | PM | [7 empty] | Done
9 | PwC | Unit Testing | 2 | 2023-01-05 | 2023-03-05 | 2023-01-05 | 2023-03-05 | Completed
|  | MM | [6 empty] | 100% | Done
|  | FICO | [6 empty] | 100% | Done
|  | SD | [6 empty] | 100% | Done
|  | PS | [6 empty] | 100% | Done
|  | PM | [6 empty] | 100% | Done
10 | PwC | Transfer to Quality System | 1 | 2023-03-05 | 2023-04-05 | 2023-03-05 | 2023-03-05 | Completed | 100%
11 | VEPL | CTM Testing (UAT/Regression Testing) | 3 | 2023-04-05 | 2023-07-05 | 2023-03-05 |  | In progress | 10%
12 | VEPL / PwC | Incident resolution and closure | 2 | 2023-07-05 | 2023-09-05 |  |  | Yet to Start
13 | VEPL / PwC | Uploading of TR Forms in VOICE Tool | 1 | 2023-10-05 | 2023-11-05 |  |  | Yet to Start
14 | VEPL | Movement of TR to PRD | 1 | 2023-11-05 | 2023-12-05 |  |  | Yet to Start
15 | VEPL | Providing of authorisation to Users | 1 | 2023-11-05 | 2023-12-05 |  |  | Yet to Start
16 | VEPL | Production Master data Maintenance | 2 | 2023-12-05 | 14-05-2023 |  |  | Yet to Start
17 |  | Ready for use in Production
User Testing
MM
FI
| PS |  | Done / UT Success mail recieved | Done / UT Success mail recieved
PM
| SD |  | Done | Done
TR No.s | Sequence | TR No.s | TR Description | TR Description | TR Forms
MM | 1.1 | DS4K901984 | MM_17102022_Plant - 3052(pench)_HN | MM_17102022_Plant - 3052(pench)_HN
| 1.2 | DS4K902237 | MM_14112022_quality inspection setting_HN | MM_14112022_quality inspection setting_HN
| 1.3 | DS4K902245 | MM_14112022_Pench 3052 name change_HN | MM_14112022_Pench 3052 name change_HN
| 1.4 | DS4K902221 | MM_10112022_Storage Location for Pench O&M 3052_RD | MM_10112022_Storage Location for Pench O&M 3052_RD
| 1.5 | DS4K902241 | MM_14112022_St Loc Change NMC PENCH O&M 3052_RD | MM_14112022_St Loc Change NMC PENCH O&M 3052_RD
FI | 2.1 | DS4K902145 | FICO_04112022_Pench Plant Configuration | FICO_04112022_Pench Plant Configuration
PS | 3.1 | DS4K902009 | PS_19102022_3052 Plant Configuration_RS | PS_19102022_3052 Plant Configuration_RS | Recieved
| 3.2 | DS4K902253 | PS_15112022_3052_CONFIG_SETTING_ZV02 | PS_15112022_3052_CONFIG_SETTING_ZV02
PM | 4.1 | DS4K902011 | PM_19102022_3052 Plant Configuration_NM | PM_19102022_3052 Plant Configuration_NM
SD | 5.1 | DS4K901990 | SD: Plant 3052 Configuration | SD: Plant 3052 Configuration
What is pending | SRN | VEPL Bhagrashree | Harshada | Harshada | Done
| Invoice Parking | VEPL Bhagrashree | Harshada | Harshada | Done
| FI Invoice Posting : SRN | VEPL : Manish Daga | Akash | Akash
| FI Invoice Posting : GRN | VEPL : Manish Daga | Akash | Akash
|  | 1 | Balance WRICEF | Balance WRICEF
|  | 2 | Balance Plants | Balance Plants
|  | 3 | Handover Documentation | Handover Documentation
|  | 4 | Incident | Incident