## Sheet1
WBS Element | Description | WBS Element | Material | Mat Des | Inventory Qty | Inventory Rate | Remaining Inv Qty | Inventory Amount | Billing % | Billing Qty | Billing Rate | Billing Amount | Consumption % | Consumption Qty | Consumption Rate | Consumption Amount | Provisional % | Provisional Qty | Provisional Rate | Provisional Amount | Qty(Adj Agst provision) | Rate(Adj Agst provision) | Value(Adj Agst provision) | Qty(Adj for Cons vs Billed) | Rate(Adj for Cons vs Billed) | Value(Adj for Cons vs Billed) | WBS2 Qty(Adj for Cons Vs to be billed) | Bal%(Adj for Cons Vs to bill) | Val(Adj for Cons Vs to bill) | WBS3 Qty(Adj for Cons Vs to bill) | WBS3 Billed %(Adj for Cons Vs to bill) | WBS3 Value(Adj for Cons Vs to bill) | WBS4 Qty(Adj for Cons Vs to bill) | WBS4 Billed %(Adj for Cons Vs to bill) | WBS4 Value(Adj for Cons Vs to bill) | Total Value(Adj for Cons Vs to bill)
E-168 | 3070-Water supply scheme project | E-168 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E-168-WS-03-01 | SUPPLY OF PIPE | E-168-WS-03-01 | 1300000338 | DI_PIPE_300 mm_K7_8329 | 2500 | 1716 | 0 | 4290000 | 70 | 2500 | 1813.7 | 4534250 | 0 | -2500 | 1716 | -4290000 | 70 | 2500 | 1716 | 3003000 | 2500 | 1716 | -3003000 | 0 | 1716 | 0 | 2500 | 10 | -429000 | 2500 | 5 | 214500 | 2500 | 5 | 214500 | 0
E-168-WS-03-02 | LAYING | E-168-WS-03-02 |  |  | 0 | 0 | 0 | 0 | 20 | 2500 | 518.2 | 1295500 | 0 | 0 | 0 | 0 | 20 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E-168-WS-03-03 | TESTING | E-168-WS-03-03 |  |  | 0 | 0 | 0 | 0 | 5 | 2500 | 129.55 | 323875 | 0 | 0 | 0 | 0 | 5 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E-168-WS-03-04 | COMMI | E-168-WS-03-04 |  |  | 0 | 0 | 0 | 0 | 5 | 2500 | 129.55 | 323875 | 0 | 0 | 0 | 0 | 5 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0